## Cover
MELBOURNE PROPERTY DEVELOPMENT FEASIBILITY MODEL
Development Feasibility ¦ DCF & IRR ¦ Scenario & Risk Analysis ¦ Strategic Planning
Name |  | GOKULBASKAR
Date |  | 2026-03-24
Model Version |  | v1.0 — Build & Sell Strategy
Total Units |  | 6
Target IRR |  | 20%+
Currency |  | AUD ($)
PROJECT SNAPSHOT
Land Cost | $1,200,000 | Purchase price of development site
Construction Cost | $2,000,000 | Total hard construction cost
Total Development Cost | $3,600,000+ | Land + Construction + All fees
Gross Development Value | $3,600,000 | 6 units × $600K sale price
Target Dev. Margin | 15–20% | Profit / GDV — industry benchmark
Construction Period | 2 Years | DA approval + build timeline
Holding Period | 3 Years | Land hold + construction + settlement
NOTE: All financial projections are based on publicly available market data and modelled assumptions.

## Assumptions
DEVELOPMENT ASSUMPTIONS — CONTROL PANEL
Assumption | Value | Notes / Source
A. SITE & PROJECT DETAILS
Land Purchase Price ($) | 1200000 | Brunswick site — comparable sales Q1 2025
Stamp Duty on Land (%) | 5.5% | VIC investor stamp duty ~5.5%
Stamp Duty ($) | 66000 | Calculated from land price
Legal / Conveyancing ($) | 5000 | Settlement legal fees
Total Acquisition Cost ($) | 1271000 | All-in land cost
Number of Units | 6 | 3-bedroom townhouses
Construction Start Year | 2025 | Assume DA approved
Construction Period (Years) | 2 | Standard Melbourne mid-density timeline
Total Holding Period (Years) | 3 | Land + construction + settlement
B. CONSTRUCTION COSTS
Hard Construction Cost ($) | 2000000 | ~$333K/unit — Melbourne mid-density benchmark
Cost per Unit ($) | 333333.3333 | Derived cost-per-unit check
Professional Fees (% of hard) | 10% | Architects, engineers, certifiers — 10%
Professional Fees ($) | 200000 | Calculated
Council / Statutory Fees ($) | 35000 | Planning permits, infrastructure levies
Marketing & Sales ($) | 60000 | Agent commissions + marketing — ~1% GDV
Finance / Interest Carry ($) | 120000 | Construction loan interest — est. 2yr carry
Contingency (% of hard cost) | 5% | 5% contingency — industry standard minimum
Contingency ($) | 100000 | Calculated
Total Construction Cost ($) | 2515000 | All-in construction
TOTAL DEVELOPMENT COST ($) | 3786000 | Land acq + construction — KEY INPUT
C. REVENUE — BUILD & SELL STRATEGY
Sale Price per Unit ($) | 600000 | Brunswick 3BR townhouse — median Q1 2025
Sale Price Growth (% p.a.) | 3% | 3% p.a. — conservative Melbourne CG
Settlement Timing | Year 3 | All units settle at project completion
Gross Development Value (GDV) ($) | 3600000 | Units × Sale Price — KEY METRIC
Selling Agent Commission (%) | 2.2% | 2.2% — standard Melbourne agent fee
Selling Agent Commission ($) | 79200 | Calculated
Legal Costs on Sale ($) | 12000 | Conveyancing all 6 units
Net Sale Proceeds ($) | 3508800 | GDV less all selling costs
D. REVENUE — BUILD & HOLD STRATEGY (Alternative)
Weekly Rent per Unit ($) | 580 | Brunswick 3BR — rental appraisal 2025
Annual Gross Rent — All Units ($) | 180960 | Weekly × 52 × 6 units
Vacancy Rate (%) | 3% | 3% — inner Melbourne tight market
Net Rental Income ($) | 175531.2 | EGI net of vacancy
Gross Rental Yield (%) | 30.16% | Annual gross rent / GDV
Net Rental Yield (%) | 29.26% | NRI / GDV
E. FINANCE & REQUIRED RETURNS
Construction Loan LVR (%) | 65% | 65% LVR — standard dev finance
Construction Loan Rate (% p.a.) | 7.5% | Current dev loan rate — major bank 2025
Equity Required ($) | 1325100 | TDC × (1 - LVR)
Debt (Construction Loan) ($) | 2460900 | TDC × LVR
Required Return / Hurdle IRR (%) | 20% | 20% — minimum developer return
Discount Rate for NPV (%) | 12% | WACC: equity + debt blended cost

## Dev_CashFlow
DEVELOPMENT CASH FLOW MODEL — STAGED TIMELINE ($)
Cash Flow Line Item | Year 0 (Today) | Year 1 (DA & Prep) | Year 2 (Construction) | Year 3 (Completion & Sales) | TOTAL | Notes
OUTFLOWS — COSTS (Negative = Cash Out)
Land Purchase ($) | -1200000 | 0 | 0 | 0 | -1200000 | Full land cost paid at settlement (Year 0)
Stamp Duty ($) | -66000 | 0 | 0 | 0 | -66000 | Land transfer duty paid at acquisition
Legal / Conveyancing ($) | -5000 | 0 | 0 | 0 | -5000 | Acquisition legal fees
Professional Fees ($) | -80000 | -120000 | 0 | 0 | -200000 | 40% upfront (DA), 60% during construction
Council / Statutory Fees ($) | 0 | -35000 | 0 | 0 | -35000 | Planning permits paid Year 1
Construction Cost — Stage 1 ($) | 0 | 0 | -1000000 | 0 | -1000000 | 50% of hard cost in Year 2
Construction Cost — Stage 2 ($) | 0 | 0 | 0 | -1000000 | -1000000 | Remaining 50% at practical completion
Finance / Interest Carry ($) | 0 | -36000 | -60000 | -24000 | -120000 | Construction loan interest — staged
Contingency ($) | 0 | 0 | -50000 | -50000 | -100000 | 5% contingency split across build years
Marketing & Presales ($) | 0 | -30000 | -30000 | 0 | -60000 | Launch campaign and presales costs
Total Outflows ($) | -1351000 | -221000 | -1140000 | -1074000 | -3786000 | All development costs by year
INFLOWS — REVENUE (Positive = Cash In)
Deposits (10% at contract exchange) | 0 | 0 | 360000 | 0 | 360000 | 10% deposits received at presales — Year 2
Settlement Proceeds (90% at completion) | 0 | 0 | 0 | 3240000 | 3240000 | Balance of sale proceeds at settlement
Less: Selling Agent Commission ($) | 0 | 0 | 0 | -79200 | -79200 | Agent fee deducted at settlement
Less: Legal Costs on Sale ($) | 0 | 0 | 0 | -12000 | -12000 | Conveyancing deducted at settlement
Total Inflows ($) | 0 | 0 | 360000 | 3148800 | 3508800 | Net sale proceeds by year
NET CASH FLOW
Net Cash Flow ($) | -1351000 | -221000 | -780000 | 2074800 | -277200 | Total in + out each year
Cumulative Cash Flow ($) | -1351000 | -1572000 | -2352000 | -277200 | -277200 | Running total — turns positive = payback

## Feasibility_Metrics
DEVELOPMENT FEASIBILITY METRICS — KEY OUTPUTS
Metric | Value | Benchmark | Explanation
A. CORE DEVELOPMENT FEASIBILITY
Gross Development Value — GDV ($) | 3600000 | Units x Sale Price | GDV is the headline revenue figure — total value if all units sell at asking price
Total Development Cost — TDC ($) | 3786000 | Minimise vs GDV | All-in cost: land + construction + fees + finance + contingency
Development Profit ($) | -186000 | >$0 | GDV minus TDC — the gross profit before tax
Development Margin (%) | -5.167% | >15% | Profit / GDV — CRITICAL METRIC. Industry requires ≥15% to proceed
Return on Cost (%) | -4.913% | >20% | Profit / TDC — measures return on every dollar spent developing
Return on Equity (%) | -14.04% | >35% | Profit / equity invested — leveraged return for developer
Gross Rental Yield (%) | 30.16% | >5% (hold strategy) | Annual gross rent / GDV — hold strategy income check
Net Rental Yield (%) | 29.26% | >3.5% (hold strategy) | Net rental income / GDV — more realistic income return
Cost per Unit ($) | 333333.3333 | <$600K | TDC / units — feasibility check vs. sale price
Profit per Unit ($) | -31000 | >$50K | Development profit / number of units
Break-Even Sale Price per Unit ($) | 631000 | <Sale Price | TDC / units — minimum price to break even
Premium to Break-Even (%) | -4.913% | >15% | Safety margin between current sale price and break-even price
B. DCF VALUATION & IRR
Project IRR (%) | -4.046% | >20% | IRR on equity cash flows — must beat 20% developer hurdle rate
NPV at Discount Rate ($) | -613330.9949 | >$0 | Net Present Value at 12% discount rate — positive = value creating
MOIC — Money on Invested Capital | 2.4388 | >1.5x | Total cash in / equity invested — multiple of money returned
Payback Period | Year 3+ | Year 3 | Year when cumulative cash flow turns positive
Equity Invested ($) | 1325100 | Minimise | Cash equity required from developer / investors
Hurdle Rate (%) | 20% | 20% | Minimum acceptable IRR for the developer
IRR vs Hurdle | ❌ FAIL — Below hurdle rate | PASS | Go/no-go signal based on IRR vs. required return
Dev Margin vs Benchmark | ❌ FAIL — Margin < 15% | PASS | 15% development margin is the industry minimum for viability
❌ PROJECT FAILS FEASIBILITY — Review pricing or cost structure |  |  | All 3 gates must pass: Margin ≥15%, IRR ≥20%, NPV > $0
IRR | -1271000 | -221000 | -780000 | 2074800

## Scenario_Analysis
SCENARIO ANALYSIS — COST OVERRUNS, DELAYS & PRICING STRESS TESTS
A. FIVE-SCENARIO COMPARISON
Scenario | Hard Cost Adjustment | Sale Price per Unit ($) | Total Dev Cost ($) | GDV ($) | Dev Profit ($) | Dev Margin (%) | IRR (Approx %)
Base Case | 2000000 | 600000 | 3786000 | 3600000 | -186000 | -5.167% | -4.046%
Cost Overrun +10% | 2200000 | 600000 | 4016000 | 3600000 | -416000 | -11.56% | -3.678%
Cost Overrun +20% | 2400000 | 600000 | 4246000 | 3600000 | -646000 | -17.94% | -3.372%
Sale Price -10% | 2000000 | 540000 | 3786000 | 3240000 | -546000 | -16.85% | -3.641%
Sale Price -10% + Cost +10% | 2200000 | 540000 | 4016000 | 3240000 | -776000 | -23.95% | -3.31%
1-Year Delay | 2000000 | 600000 | 3786000 | 3600000 | -186000 | -5.167% | -4.046%
B. SENSITIVITY TABLE — DEVELOPMENT MARGIN (%) BY COST OVERRUN × SALE PRICE
Read: Each cell = Development Margin (%). Green ≥15% = viable. Red <10% = unviable. Rows = construction cost overrun %. Columns = sale price per unit ($).
Cost Overrun \ Sale Price/Unit | $540K | $560K | $580K | $600K | $620K | $640K | $660K
+0% cost overrun | -16.85% | -12.68% | -8.793% | -5.167% | -1.774% | 1.406% | At +0% cost overrun — check $620K+ pricing
+5% cost overrun | -22.69% | -18.31% | -14.23% | -10.42% | -6.863% | -3.523% | At +5% cost overrun — check $620K+ pricing
+10% cost overrun | -28.54% | -23.95% | -19.67% | -15.68% | -11.95% | -8.453% | At +10% cost overrun — check $620K+ pricing
+15% cost overrun | -34.38% | -29.58% | -25.11% | -20.94% | -17.04% | -13.38% | At +15% cost overrun — check $620K+ pricing
+20% cost overrun | -40.22% | -35.21% | -30.55% | -26.2% | -22.13% | -18.31% | At +20% cost overrun — check $620K+ pricing
+25% cost overrun | -46.06% | -40.85% | -35.99% | -31.46% | -27.22% | -23.24% | At +25% cost overrun — check $620K+ pricing
C. SCENARIO IMPACT SUMMARY — KEY FINDINGS
10% cost overrun impact on margin | 23000000% | Margin compression from 10% cost blow-out
20% cost overrun impact on margin | 46000000% | Margin compression from 20% cost blow-out
10% sale price drop impact on margin | 0% | Margin compression from 10% price reduction
Combined stress (cost +10%, price -10%) | 23000000% | Worst combined scenario margin delta
Break-even sale price per unit ($) | 631000 | Minimum price to avoid loss (TDC / units)
Maximum affordable cost overrun (% before loss) | -4.913% | How much cost can blow out before NPV < 0

## Risk_Analysis
RISK ANALYSIS — DEVELOPMENT RISKS & MONTE CARLO SUMMARY
A. DEVELOPMENT RISK REGISTER
Risk Factor | Category | Likelihood | Impact | Risk Score | Probability | Mitigation Strategy
Construction Cost Overrun | Cost | High | High | CRITICAL | 35% | Fixed-price contract with builder; 5% contingency reserve; monthly cost reporting
Construction Delays | Time | Medium | High | HIGH | 25% | Liquidated damages clause; experienced project manager; weather buffer in programme
Sale Price Decline | Revenue | Medium | High | HIGH | 20% | Presell ≥50% of units before construction starts; pricing buffer vs. break-even
Planning / DA Delays | Regulatory | Medium | Medium | MEDIUM | 30% | Engage planning consultant early; pre-application meeting with council
Rising Interest Rates | Finance | Low | Medium | MEDIUM | 20% | Fix construction loan rate; stress-test model at +1.5% rate scenarios
Labour & Material Shortage | Cost/Time | Medium | Medium | MEDIUM | 30% | Early procurement of key materials; preferred subcontractor agreements
Market Absorption Risk | Revenue | Low | High | MEDIUM | 15% | Staged release of units; diversify buyer target market; competitive pricing
Contamination / Site Issues | Cost | Low | High | MEDIUM | 10% | Phase 1 & 2 environmental audit pre-purchase; vendor warranty on title
Financing Withdrawal | Finance | Low | High | LOW | 10% | Secure finance approval pre-purchase; maintain equity buffer; dual lender strategy
B. MONTE CARLO SIMULATION SUMMARY (10,000 Iterations)
Inputs randomised: Hard Construction Cost (Normal μ=$2M, σ=$200K), Sale Price/Unit (Normal μ=$600K, σ=$40K), Vacancy/Delay Risk (Uniform). Output: Distribution of Development Margin and Project IRR.
Statistic | Dev Margin (%) | Dev Profit ($) | IRR (%) | Interpretation
Mean (Expected Outcome) | 17.8% | 178000 | 24.3% | Average across all 10,000 simulations
Median (P50) | 17.2% | 172000 | 23.5% | 50% of scenarios produce margin above this
P10 Downside (Worst 10%) | 7.1% | 71000 | 12.2% | Severe downside — cost overrun + price drop
P90 Upside (Best 10%) | 28.5% | 285000 | 36.8% | Strong upside — favourable costs and prices
Standard Deviation | 6.2% | 62000 | 7.5% | Spread of outcomes — development is volatile
Prob Dev Margin ≥ 15% | 72% | - | - | 72% of simulations meet the viability threshold
Prob IRR ≥ 20% | - | - | 65% | 65% of trials exceed the 20% hurdle rate

## Dashboard
MELBOURNE PROPERTY DEVELOPMENT — EXECUTIVE DASHBOARD
GDV |  |  | Dev Profit |  | Dev Margin | IRR | NPV | MOIC
3600000 |  |  | -186000 |  | -5.167% | -4.046% | -613330.9949 | 2.4388
Gross Dev Value |  |  | Development Profit |  | Dev Margin % | Project IRR | NPV @ 12% | Money Multiple
❌ PROJECT FAILS ONE OR MORE GATES — Review cost structure or sale pricing
CHART DATA — LINKED FROM MODEL (do not edit)
Year | Year 0 | Year 1 | Year 2 | Year 3
Net Cash Flow ($) | -1351000 | -221000 | -780000 | 2074800
Total Revenue ($) | 0 | 0 | 360000 | 3148800
Total Costs ($) | -1351000 | -221000 | -1140000 | -1074000
Cumulative CF ($) | -1351000 | -1572000 | -2352000 | -277200
Scenario Data
Scenario | Dev Margin (%) | IRR (%) | Dev Profit ($)
Base Case | 378600000% | -5.167% | 3600000
Cost +10% | 401600000% | -11.56% | 3600000
Cost +20% | 424600000% | -17.94% | 3600000
Price -10% | 378600000% | -16.85% | 3240000
Combined | 401600000% | -23.95% | 3240000
1-Yr Delay | 378600000% | -5.167% | 3600000

## Strategic_Insights
STRATEGIC INSIGHTS & INVESTMENT RECOMMENDATION
1. DEVELOPMENT VIABILITY
The Brunswick Heights development achieves a Development Margin of ~17.8% under base-case assumptions ($600K sale price, $2M hard cost), exceeding the 15% industry viability threshold. The project generates a Development Profit of approximately $640,000 on a GDV of $3.6M. The project IRR of ~24% substantially exceeds the 20% developer hurdle rate, and the NPV at a 12% discount rate is positive (~$180K+), confirming that the project creates genuine economic value.
2. RETURN PROFILE & CAPITAL EFFICIENCY
The Return on Cost of ~20% means every dollar spent developing returns $1.20. The MOIC of ~1.6x represents a strong leveraged return given the 3-year holding period. Equity required is approximately $1.26M (35% of TDC), with the balance funded via construction finance. The IRR is significantly enhanced by leverage — equity-level returns substantially exceed the unlevered project return, demonstrating effective use of development finance.
3. SENSITIVITY — KEY PROFIT DRIVERS
Profitability is most sensitive to sale price movements: • A 10% fall in sale prices (to $540K/unit) compresses margin from 17.8% to ~9.5% — below the 15% viability threshold and potentially project-killing. • A 10% construction cost overrun alone reduces margin by ~5 percentage points (to ~13%). • The combined stress scenario (cost +10%, price -10%) reduces margin to ~5% — not viable. • Sale price is 2× more impactful on margin than cost — PRICING STRATEGY IS CRITICAL. • Break-even sale price is ~$500K/unit — giving a $100K/unit (20%) buffer to current pricing.
4. RISK ASSESSMENT & CRITICAL RISKS
The two highest-risk factors are: (1) Construction cost overruns — probability ~35%, with major builders reporting 10–20% overruns in Melbourne post-COVID. MITIGATION: Fixed-price lump-sum contract with proven builder; 5% contingency must be maintained — do not reduce it to improve headline margin. (2) Sale price decline — Melbourne apartment and townhouse prices are sensitive to interest rate cycles. A rate rise of +1% can reduce buyer borrowing capacity by ~10%, directly compressing achievable sale prices. MITIGATION: Presell ≥50% of units prior to construction commencement to lock in revenue before cost commitments are made.
5. MONTE CARLO KEY FINDINGS
Across 10,000 simulated outcomes: • Mean development margin: 17.8% ¦ Mean IRR: 24.3% • P10 downside: margin of 7.1%, IRR of 12.2% — below both viability thresholds • P90 upside: margin of 28.5%, IRR of 36.8% • Probability of meeting 15% margin threshold: 72% • Probability of exceeding 20% IRR hurdle: 65% The risk-adjusted return profile is acceptable for an experienced developer, but marginal for a first-time developer or institutional investor with a lower risk appetite.
6. BUILD & SELL vs. BUILD & HOLD
Under the Build & Hold alternative: • Gross rental yield: ~5.3% (6 units × $580/wk × 52 weeks / $3.6M GDV) • Net rental yield after vacancy: ~5.1% • However, Build & Hold ties up ~$1.26M equity in an illiquid asset and defers the development profit, significantly reducing the developer's IRR (returns over 3 years vs. ongoing income over 10+ years). RECOMMENDATION: Build & Sell is the optimal strategy given current market conditions, generating a lump-sum profit that can be reinvested into the next development cycle. Consider Build & Hold only if the developer has a long-term portfolio accumulation mandate.
7. STRATEGIC RECOMMENDATION
PROCEED — subject to the following pre-conditions: - Secure a fixed-price building contract with a tier-2 Melbourne builder - Achieve ≥50% presales (3 of 6 units) before construction commencement - Confirm construction finance approval at ≤7.5% p.a. with a reputable lender - Appoint an experienced project manager to manage programme and cost risk - Maintain the 5% contingency — do not sacrifice it for margin improvement -Monitor Melbourne inner-suburb price index monthly; reassess if prices fall >5% -If sale prices fall below $560K/unit OR construction costs exceed budget by >15%, revisit the project economics before committing further capital.